## Sheet1
ERP REQUIREMENTS REGISTER – CULINOVA ERP OPTIMIZATION PROJECT
Phase 1 – ERP Optimization & Operational Control
MILESTONE 1 – SYSTEM AUDIT, SECURITY & GOVERNANCE
ID | Module | Requirement | Business Impact | Priority
SEC-001 | User Permissions | Sales users cannot modify selling prices without authorization. | Protect margins and pricing policy. | Critical
SEC-002 | User Permissions | Discount limits by user role. | Prevent unauthorized discounts. | Critical
SEC-003 | User Permissions | Discounts above threshold require manager approval. | Commercial control. | Critical
SEC-004 | User Permissions | Cost and profitability data hidden from Sales users. | Protect confidential financial information. | Critical
SEC-005 | Sales Orders | Approved Sales Orders cannot be modified without approval workflow. | Change management control. | Critical
SEC-006 | Inventory | Reserved stock cannot be released without Operations approval. | Prevent stock conflicts. | Critical
SEC-007 | Audit Trail | Track all modifications to quotations, SOs, POs, pricing and stock reservations. | Accountability and traceability. | Critical
MILESTONE 2 – ITEM MASTER & INVENTORY STRUCTURE
Item Master
ID | Requirement | Business Impact | Priority
IM-001 | Remove duplicate items. | Data accuracy. | Critical
IM-002 | Standard item naming convention. | Consistency. | Critical
IM-003 | Standard item coding convention. | Traceability. | Critical
IM-004 | Supplier Code Mapping. | Procurement control. | Critical
IM-005 | Dynamic item description generation. | Faster item creation. | High
IM-006 | Mandatory Sub Item Group. | Data quality. | High
IM-007 | Item templates for duplication. | Faster item creation. | High
IM-008 | Standardized product image dimensions. | Professional presentation. | Medium
IM-009 | Hide disabled items from operational documents. | Prevent selection errors. | High
IM-010 | Support special-design/custom equipment items. | Project flexibility. | High
Inventory Visibility
ID | Requirement | Business Impact | Priority
INV-001 | Show Physical Stock Quantity. | Stock visibility. | Critical
INV-002 | Show Reserved Quantity. | Prevent overselling. | Critical
INV-003 | Show Available Quantity. | Better sales decisions. | Critical
INV-004 | Show Incoming Purchase Quantity. | Procurement visibility. | High
INV-005 | Show stock aging (days in inventory). | Inventory optimization. | High
INV-006 | Auto stock reservation on approved SO. | Inventory control. | Critical
INV-007 | Reservation release approval workflow. | Stock governance. | Critical
INV-008 | Visibility of stock availability in quotations. | Commercial accuracy. | Critical
INV-009 | Visibility of stock availability in BOQ preparation. | Project planning. | High
MILESTONE 3 – FINANCE, COSTING & CASH FLOW
ID | Requirement | Business Impact | Priority
FIN-001 | Landed Cost Allocation. | Accurate profitability. | Critical
FIN-002 | Freight allocation. | True cost visibility. | Critical
FIN-003 | Customs allocation. | True cost visibility. | Critical
FIN-004 | SABER allocation. | True cost visibility. | Critical
FIN-005 | Clearance allocation. | True cost visibility. | Critical
FIN-006 | Storage allocation. | True cost visibility. | Critical
FIN-007 | Internal transportation allocation. | True cost visibility. | Critical
FIN-008 | Certificate of Origin allocation. | True cost visibility. | High
FIN-009 | Bank transfer cost allocation. | True cost visibility. | High
FIN-010 | Exchange rate variance tracking. | Profitability accuracy. | Critical
FIN-011 | True Product Costing. | Pricing decisions. | Critical
FIN-012 | Project Estimated Cost Calculation. | Project planning. | Critical
FIN-013 | Project Actual Cost Calculation. | Profitability analysis. | Critical
VAT & Invoicing
ID | Requirement | Business Impact | Priority
VAT-001 | Customer advance invoice management. | VAT compliance. | Critical
VAT-002 | Customer advance invoice reconciliation. | Prevent double VAT. | Critical
VAT-003 | Final invoice offset against advance invoices. | Compliance. | Critical
VAT-004 | Supplier advance invoice management. | Payables control. | Critical
VAT-005 | Supplier advance invoice reconciliation. | VAT compliance. | Critical
VAT-006 | Visibility of advance payments in reports. | Financial visibility. | Critical
Cash Flow
ID | Requirement | Business Impact | Priority
CF-001 | Cash Flow Forecast Dashboard. | Financial planning. | Critical
CF-002 | Forecast customer collections. | Liquidity visibility. | Critical
CF-003 | Forecast supplier payments. | Cash planning. | Critical
CF-004 | Forecast project obligations. | Operational planning. | High
CF-005 | Include salaries. | Complete cash flow. | Critical
CF-006 | Include office rent. | Complete cash flow. | Critical
CF-007 | Include warehouse rent. | Complete cash flow. | Critical
CF-008 | Include recurring expenses. | Complete cash flow. | Critical
CF-009 | 30/60/90-day forecast. | Executive planning. | Critical
MILESTONE 4 – SALES, PROCUREMENT, PROJECTS & DELIVERY
Sales & CRM
ID | Requirement | Business Impact | Priority
CRM-001 | Auto assign salesperson. | Data consistency. | High
CRM-002 | Customer pricing history. | Better pricing decisions. | High
CRM-003 | Customer discount history. | Commercial control. | High
CRM-004 | Quotation status workflow. | Pipeline visibility. | Critical
CRM-005 | Sent status. | Pipeline visibility. | High
CRM-006 | Under Negotiation status. | Pipeline visibility. | High
CRM-007 | Rejected status. | Pipeline visibility. | High
CRM-008 | Alternative Quotation Management | Pipeline visibility. | Medium
Sales Order
ID | Requirement | Business Impact | Priority
SO-001 | Auto transfer lead time from quotation. | Delivery accuracy. | High
SO-002 | Auto transfer Area & Position. | Project control. | High
SO-003 | Dual discount support (percentage + fixed amount). | Commercial flexibility. | High
SO-004 | Show stock availability. | Better planning. | Critical
SO-005 | Project estimated cost visibility. | Profitability visibility. | Critical
SO-006 | Line-level fulfillment tracking. | Project execution control. | Critical
SO-007 | Item-Level Procurement, Inventory & Delivery Status Tracking | Full project execution visibility. | Critical
Procurement
ID | Requirement | Business Impact | Priority
PO-001 | Supplier code mapping in PO. | Procurement accuracy. | Critical
PO-002 | Exchange rate recorded at payment stage. | Financial accuracy. | High
PO-003 | PO submission before payment. | Operational flexibility. | High
PO-004 | Supplier performance dashboard. | Vendor management. | High
Delivery & Projects
ID | Requirement | Business Impact | Priority
DEL-001 | Area & Position in Delivery Note. | Delivery accuracy. | High
DEL-002 | Customer signature attachment. | Delivery proof. | Critical
DEL-003 | Customer acceptance workflow. | Project control. | Critical
DEL-004 | Delivery rejection workflow. | Inventory accuracy. | Critical
DEL-005 | Return authorization process. | Traceability. | Critical
DEL-006 | Pre-Delivery Readiness Report. | Customer coordination. | High
DEL-007 | Pre-Delivery Payment Claim. | Faster collections. | Critical
DEL-008 | Operational Completion %. | Project visibility. | Critical
DEL-009 | Financial Completion %. | Project visibility. | Critical
DEL-010 | Delivered Value %. | Project visibility. | Critical
DEL-011 | Collection Progress %. | Financial visibility. | High
MILESTONE 5 – DASHBOARDS, KPI & MANAGEMENT REPORTING
Executive Dashboards
ID | Requirement | Priority
KPI-001 | Executive Dashboard | Critical
KPI-002 | Financial Dashboard | Critical
KPI-003 | Sales Dashboard | Critical
KPI-004 | Procurement Dashboard | High
KPI-005 | Inventory Dashboard | Critical
KPI-006 | Project Dashboard | Critical
KPI-007 | Cash Flow Dashboard | Critical
KPI-008 | Delayed Projects Dashboard | High
Customer 360
ID | Requirement | Priority
C360-001 | Total Quotations | High
C360-002 | Total Sales Orders | High
C360-003 | Total Project Value | High
C360-004 | Conversion Rate | High
C360-005 | Discount History | High
C360-006 | Outstanding Balance | Critical
Supplier 360
ID | Requirement | Priority
S360-001 | Total Purchases | High
S360-002 | Purchase History | High
S360-003 | Discount History | High
S360-004 | Lead Time Analysis | High
S360-005 | Outstanding Balance | Critical
HR & EMPLOYEE PORTAL
ID | Requirement | Priority
HR-001 | Employee Leave Workflow | Medium
HR-002 | Employee Email Integration | Medium
HR-003 | Salary Slip Distribution | Medium
HR-004 | Employee Advance Request Workflow | High
HR-005 | Advance Approval Workflow | High
HR-006 | Advance Repayment Tracking | High
HR-007 | Employee Outstanding Advance Balance | High
HR-008 | Commission Tracking | High
HR-009 | Expected Commission Tracking | High
HR-010 | Earned Commission Tracking | High
HR-011 | Paid Commission Tracking | High
HR-012 | Sales Target Management | High
HR-013 | Employee Performance Dashboard | High
HR-014 | Sales Achievement % | High
HR-015 | Conversion Rate by Salesperson | High